SFDP Health Innovation Challenge for Students and Young Professionals

Tagline: Fast ideas. Real impact. Young changemakers.

Organizer: Society for Disease Prevention (SFDP)

Target participants: Students and Young professionals (Teams of 3–5 members)

Competition timeline: Monday, December 25th, 2025 – Thursday, February 5th, 2026

Prizes: Top 3 teams – $300 each to implement winning project idea

Rationale

Through the Health Innovation Contest, SFDP aims to support the implementation of innovative public health project ideas developed by students and young professionals. This is for young individuals with bold, low-cost, practical ideas that can be implemented on a small scale to demonstrate action, learning, and community engagement around public health challenges in Nigeria.

Scope/Focus Areas

Teams may submit ideas that fit one or more of the following areas:

- Community-based prevention of infectious diseases (malaria, Lassa fever, TB, Hepatitis B/C)

- Vaccine uptake and hesitancy reduction

- Water, sanitation & hygiene (WASH) interventions

- Digital health for health education, screening, referral, or monitoring

- Antimicrobial resistance (community stewardship or awareness)

- Public health interventions focused on key populations disproportionately affected by health inequities,

- Maternal, newborn & child health (low-cost screening or referral solutions)

- Mental health access and peer-support models for youth

- Health data collection, community surveillance and CHW empowerment

Proposals outside these areas will be considered if they offer clear public health benefit and are feasible.

Eligibility & Team Composition

- A team of 3-5 persons (students or young professionals).

- All team members must be below 28 years of age.

- At least two team members must be in a health-focused degree or career. i.e. They must be affiliated with a health-related university course or organization in Nigeria.

- Single one-page proposal (template provided), along with CV and a short bio/profile of each team member.

- Teams can submit only one proposal.

- Projects are expected to be modest in scope and achievable within a short implementation window; large-scale service delivery or system-level interventions are not expected.

- Projects must be ethical, non-commercial, and suitable for small-scale implementation.

Ineligible: Teams already implementing the same project or those requesting funding for capital-intensive projects.

Competition Structure & Stages

Stage 1: Call for One-Page Proposals (Dec 25th, 2025 – Jan 11th, 2026)

- Dec 21st, 2025: Call opens. Teams submit a one-page proposal + CV and short profile of each team member.

- Jan 11th, 2026 (23:59 GMT+1): Submission deadline.

Stage 2: Screening & Shortlisting Top 10 (Jan 12th – Jan 18th, 2026)

- Review of submissions and shortlisting of top 10 for announcement.

Stage 3: Video Pitch Production (Jan 19th – Jan 25th, 2026)

- Teams record a video pitch of 30 seconds – 1 minute and submit for upload.

- Team members will also submit their pictures, to be used for flyer design.

Stage 4: Video Upload & Voting Period (Jan 26th – Feb 1st, 2026)

- Jan 26th, 2026: SFDP uploads all 10 videos across social platforms (IG/Facebook/Twitter/TikTok). Each video will be uploaded along with the team flyer. Voting commences, based on likes/comments/follows.

- Feb 1st, 2026: Voting ends.

Stage 5: Verification & Announcement of Results (Feb 2nd – Feb 5th, 2026)

- Feb 2nd – Feb 4th, 2026: SFDP runs verification to select winners.

- Feb 5th, 2026: Announcement of Top 3 winners.

Prize Disbursement & Project Launch (Feb 6th – Feb 12th, 2026)

- Feb 6th, 2026: Signing memorandum of agreement (MoA), sending of account details.

- Feb 7th – Feb 8th, 2026: Disbursement of $200 to each winner (wire/transfer/mobile money).

- Feb 12th, 2026: Implementation phase begins after disbursement (timeframe of 2 months).

Proposal Submission Template

Team proposals must be one page (A4) and include:

- Project title (20 words max)

- Team name and Contact of team lead (name, email, phone number)

- Problem statement

- Proposed innovation/solution

- Target population & location

- Key activities and simple timeline

- Impact & how success will be measured (2–3 KPIs)

(Each team member must also submit their CV and short bio/profile)

Selection Criteria & Scoring (to shortlist top 10)

- Relevance to public health need (0–5)

- Clarity and feasibility of idea with $200 (0–5)

- Innovativeness / creativity (0–5)

- Potential impact and measurement (0–5)

- Team capacity (0–5)

Max screening score = 25

Engagement Metrics for Public Voting (weighted):

- Likes / reactions (weight 30%)

- Comments (weight 20%)

- Shares / reposts (weight 10%)

- New followers generated on SFDP channel linked to the post (weight 40%)

Disbursement Process

- Winners will sign a memorandum of agreement (MoA) describing funding conditions, deliverables, and reporting expectations.

- SFDP will disburse via bank transfer or mobile money to the team lead’s account within 5 business days of signed MoA.

- Teams must submit pictures/videos and a short summary report as proof of their project being implemented and completed.

Implementation & Reporting

Projects should be implemented a maximum of 2 months after disbursement (Mar–April 2026). Below is a suggested timeline:

- Week 1: Project planning starts, necessary items are procured.

- Week 2–4: Implementation of the main project activities.

- Week 5–6: Monitoring of outcomes/impact of the project (collect data, feedback, etc).

- Week 7–8: Finalise all activities related to the project.

- Within 2 weeks of completion: Submit final report (2-5 pages), along with media (videos and photos) captured during the project.

Post-Competition Engagement
Following the competition, SFDP may engage selected participants as volunteers or ambassadors for future outreach, health education, or innovation-related activities. This engagement is informal and non-funded, aimed at sustaining visibility, learning, and youth participation beyond the competition cycle.

Budget for Implementing Competition

| Item | Cost (USD) |
| --- | --- |
| Prizes (3 x $200) | 600 |
| Design of flyers | 42 |
| Social media ads | 30 |
| Zoom subscription | 20 |
| Support for 2 Reviewers |  |
| Contingency / Miscellaneous |  |
| Total (tentative base) | 692 |